## Sheet1
	GLK	correction	Total	ST	Import	Total
Active	3967	16	3983	3983		3983
Published	12536		12536	2427	6248	8675
Unresolved	2118	-16	2102	584	1291	1875
Deprecated	1		1	1		1
Total			18622	6995	7539	14534

	Diff	Percentage
Active	0	100.00%
Published	3861	69.20%
Unresolved	227	89.20%
Deprecated	0	100.00%
Total	4088	78.05%

## Sheet2
Failed Mappings
Reason	Total	Database
		barda	gcv	giv	giv2	giv3	hrv2	jev	mmp	piv	rtv	swiv	yfv
Subtasks left open	136	5			51				2			78
Final status miss-match	623		58	135	2	266		1		36	2	122	1
Status=Final Check	155		12	10					133
Status=Recalled	133			133
Status=Avian Varied Subtype	89			89
Status=XX-Avian	24			24
Status=Reassembly\n	2			2
Status=Resequencing	2627			868		45					1714
Status=Next Gen Complete	61					61
Initials=Design	226			113	10	103
Initials=Hold	5			5
Invalid collection	112					112

Totals	4193	5	70	1379	63	414	112	1	2	36	196	1914	1

## Sheet3
Key		Summary		Status	Assignee	Created	Updated
STS-5		Command Line tool to Edit fields in JIRA		In Progress	Nadia Fedorova	22/Feb/12	06/Apr/12
STS-18		Migration		Open	Peter Edworthy	30/Mar/12	30/Nov/12
STS-25		Cron to copy batch ids from GLK to Jira ST		Open	Peter Edworthy	09/May/12	30/Aug/12
STS-31		45 day hold of samples		Open	Peter Edworthy	04/Jun/12	04/Jun/12
STS-33		Delete batch_id of Unresolved and Deprecated samples		Open	Peter Edworthy	13/Jun/12	13/Jun/12
STS-46		Produce Tuple file of samples in a given state		Open	Peter Edworthy	19/Oct/12	19/Oct/12
STS-75		Remove CTM Dependancy: flap		Open	Peter Edworthy	30/Nov/12	05/Apr/13
STS-85		Taxon ID maintenance in Jira ST		Open	Peter Edworthy	07/Dec/12	26/Apr/13
STS-86		Check for pre-existing Org Names/sequences in GenBank prior to Taxon id request		Open	Peter Edworthy	07/Dec/12	07/Dec/12
STS-89		sample-move with tuple file		Open	Peter Edworthy	01/Feb/13	06/Feb/13
STS-92		Remove restriction on moving samples to Unresolved or deprecated		Open	Rebecca Halpin	29/Apr/13	29/Apr/13
STS-49		Search for multiple Blinded Numbers / Sample Numbers		Open	Peter Edworthy	26/Nov/12	07/Dec/12
	STS-64	STS-6 SQL - fl_status_sql & SDI0708_status_sql / Input: <sample names> / Output: <Sample names> <BAC ID> <status>	49	Open	Peter Edworthy	30/Nov/12	07/Dec/12
STS-50		Report grouped by Collection / Lot ID		In Progress	Peter Edworthy	26/Nov/12	07/Dec/12
STS-51		Quick Aggregate Reports		In Progress	Peter Edworthy	26/Nov/12	07/Dec/12
	STS-59	STS-6 Report - CTM Navigation Page - Side bar	50,51	Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-62	STS-6 SQL - closure_status_count / Input: <Collection Code> / Output: <status> <count>	50,51	Reopened	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-67	STS-6 Nadia - B2 / get total number of samples from a given collection in each queue	50,51	Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-70	STS-6 Nadia - F / to get a number of closure subtasks (by type) for a list of samples (tuple list of samples) or (all samples in a given collection)	50,51	Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-71	STS-6 CTMBACs - 5	50,51	Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-72	STS-76 Collection Report - Status Overview	50,51	Open	Peter Edworthy	30/Nov/12	07/Dec/12
STS-52		Comment, Comment Date Custom Field		Open	Peter Edworthy	26/Nov/12	07/Dec/12
	STS-63	STS-6 SQL - comment / Input: <BAC IDs> / Output: <BAC ID> <Comment> <date of Comment>	52	Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-68	STS-6 Nadia - C / to get comments (all comments or only the latest) for a list of samples (tuple file)	52	Open	Peter Edworthy	30/Nov/12	07/Dec/12
STS-53		State Change Date Issue Navigator Column		Open	Peter Edworthy	26/Nov/12	07/Dec/12
	STS-65	STS-6 SQL - validation_q / Input: <date range> <status> / Output: <BAC ID>	53	Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-66	STS-6 SQL - validation_q2 / Input: <date range> <status> <not deprecated> / Output: <Collection ID> <BAC ID> <Date of Change>	53	Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-69	STS-6 Nadia - E / to get a date when a sample (tuple list of samples) or (all samples in a given collection) or (all samples) were moved to a given queue (status)	53	Open	Peter Edworthy	30/Nov/12	07/Dec/12
STS-80		Days Since Most Recent Update		Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-58	STS-6 Report - CTM Navigation Page - Table	80	Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-73	STS-76 Collection Report - Overdue Samples	80	Open	Peter Edworthy	30/Nov/12	07/Dec/12
STS-81		Search for and Display 'Assigned By'		Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-60	STS-6 Report - CTM Task Manager	52,80,81	Open	Peter Edworthy	30/Nov/12	07/Dec/12
STS-82		Min and Max Dates in Reports		Open	Peter Edworthy	30/Nov/12	07/Dec/12
	STS-61	STS-6 Report - CTM Task Counts	50,51,82	Open	Peter Edworthy	30/Nov/12	07/Dec/12